## Sheet1
Working Process |  |  |  |  | Thong Nguyen (Jason) | s3769688@student.rmit.edu.au
[5 empty] | Yuepeng Du (Alan) | s3698728@student.rmit.edu.au
[5 empty] | Phan Gia Bao Le (Stephen) | s3688102@student.rmit.edu.au
Meeting on 11/9/2020
Work | Student | Plan | On Processing | Finished
Read and understand the description | Thong Nguyen (Jason) |  |  | x
Read and understand the description | Yuepeng Du (Alan) |  |  | x
Read and understand the description | Phan Gia Bao Le (Stephen) |  |  | x
Group Formed | Thong Nguyen (Jason), Yuepeng Du (Alan), Phan Gia Bao Le (Stephen) |  |  | x
MS Team created | Thong Nguyen (Jason) |  |  | x
Git Repo created | Thong Nguyen (Jason) |  |  | x
Basic Main menu with "credits" | Yuepeng Du (Alan) |  | x
Choice of where to use linked list, vector & array | Thong Nguyen (Jason), Phan Gia Bao Le (Stephen) |  | x
Main Menu | Yuepeng Du (Alan) |  | x
Meeting on 14/9/2020
Work | Student | Plan | On Processing | Finished
Basic Main menu with "credits" | Yuepeng Du (Alan) |  |  | x
Choice of where to use linked list, vector & array | Thong Nguyen (Jason), Phan Gia Bao Le (Stephen) |  |  | x
Main Menu | Yuepeng Du (Alan) |  |  | x
Implement Node class | Yuepeng Du (Alan) |  |  | x
Implement Linked List class | Yuepeng Du (Alan) |  |  | x
Implement Turn class | Yuepeng Du (Alan) |  |  | x
Implement Round class in general | Phan Gia Bao Le (Stephen) |  |  | x
Implement Mosaic class in general | Phan Gia Bao Le (Stephen) |  |  | x
Implement CalculateScore class in general | Phan Gia Bao Le (Stephen) |  |  | x
Implement Player class in general | Thong Nguyen (Jason) |  |  | x
Implement Game class in general | Thong Nguyen (Jason) |  |  | x
Implement Factories class in general | Thong Nguyen (Jason) |  |  | x
Meeting on 19/9/2020
Work | Student | Plan | On Processing | Finished
Implement Node class | Yuepeng Du (Alan) |  |  | x
Implement Linked List class | Yuepeng Du (Alan) |  |  | x
Implement Turn class | Yuepeng Du (Alan) |  |  | x
Implement Round class in general | Phan Gia Bao Le (Stephen) |  |  | x
Implement Mosaic class in general | Phan Gia Bao Le (Stephen) |  |  | x
Implement CalculateScore class in general | Phan Gia Bao Le (Stephen) |  |  | x
Implement Player class in general | Thong Nguyen (Jason) |  |  | x
Implement Game class in general | Thong Nguyen (Jason) |  |  | x
Implement Factories class in general | Thong Nguyen (Jason) |  |  | x
Meeting on 26/9/2020
Work | Student | Plan | On Processing | Finished
Implement Score (Calculate Score when done each round) | Yuepeng Du (Alan), Thong Nguyen (Jason) |  |  | x
Implement Loading game feature | Phan Gia Bao Le (Stephen) |  |  | x
Updates all group documents | Yuepeng Du (Alan) |  |  | x
Write tests cases for common uses | Yuepeng Du (Alan) |  | x
Bug fixes of Choosing the empty line, full line - Mosaic (Should be error) | Thong Nguyen (Jason) |  |  | x
Bug fixes of Same colour (What if user put the different colours in titles) | Thong Nguyen (Jason) |  |  | x
Implement Player class in details | Phan Gia Bao Le (Stephen) |  |  | x
Implement Game class in details | Phan Gia Bao Le (Stephen) |  |  | x
Meeting on 3/10/2020
Work | Student | Plan | On Processing | Finished
Bug fixes of clear the broken line after each round | Thong Nguyen (Jason) |  | x
Bug fixes of miscalculation in score | Yuepeng Du (Alan),Thong Nguyen (Jason) |  | x
Group report written | Yuepeng Du (Alan) |  | x
Fully complete implementation and error free | Thong Nguyen (Jason) |  | x
Full error checking of user prompt | Thong Nguyen (Jason) |  | x
Bug fixes in loading game | Phan Gia Bao Le (Stephen) |  | x
Fully complete implementation and error free | Thong Nguyen (Jason) |  | x
Final Tests | Phan Gia Bao Le (Stephen) |  | x
Automated placement of tiles at end of round, but no scoring | Phan Gia Bao Le (Stephen) |  | x