## Sheet1
COSC1076 ¦ Semester 2 2020
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | APT_A2 |  | Progress Classes: | Ahead
Group Member: | Phan Gia Bao Le | s3688102@student.rmit.edu.au |  | On-track
Group Member: | Yuepeng Du | s3698728@student.rmit.edu.au |  | Behind
Group Member: | Thong Nguyen | s3769688@student.rmit.edu.au |  | Way Behind
Tutor: | Dale Stanbrough | Rob Tirtasentana
Class: | Thursday 2:30 | Thursday 18:30
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Phan Gia Bao Le | Yuepeng Du | Thong Nguyen
|  |  | Group Formed |  | Weekly Contribution | Choice of where to use linked list, vector & array | Basic Main menu with "credits", Main menu | MS Team created, Git Repo created, Choice of where to use linked list, vector & array
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
Basic Main menu with "credits"
Choice of where to use linked list, vector & array
|  | Progress | Ahead
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Phan Gia Bao Le | Yuepeng Du | Thong Nguyen
|  |  | Initial Design of ADTs (classes and potential methods) |  | Weekly Contribution | Initial Design of ADTs (classes and potential methods), User Prompt (for gameplay), but no/minimal error checking, Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required, ADT implementation for storing information, game loop logic not required | Initial Design of ADTs (classes and potential methods) User Prompt (for gameplay), but no/minimal error checking Linked List implementation Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required ADT implementation for storing information, game loop logic not required Initial Design of ADTs (classes and potential methods) User Prompt (for gameplay), but no/minimal error checking Linked List implementation Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required ADT implementation for storing information, game loop logic not required Initial Design of ADTs (classes and potential methods), User Prompt (for gameplay), but no/minimal error checking, Linked List implementation, Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required, ADT implementation for storing information, game loop logic not required | Initial Design of ADTs (classes and potential methods), User Prompt (for gameplay), but no/minimal error checking, Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required, ADT implementation for storing information, game loop logic not required
|  |  | Main menu |  | Issues
|  |  | User Prompt (for gameplay), but no/minimal error checking |  | Other Notes
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | Ahead
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Phan Gia Bao Le | Yuepeng Du | Thong Nguyen
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | Implement Player class in details, Implement Game class in details, Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic, Initialisation of data strctures for new game, Loading game feature. | Updates all group documents, Implement Score (Calculate Score when done each round) | Bug fixes of Choosing the empty line, full line - Mosaic (Should be error), Bug fixes of Same colour (What if user put the different colours in titles), Implement Score (Calculate Score when done each round), Save game feature
|  |  | Initialisation of data strctures for new game |  | Issues
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic
|  | Progress | Ahead
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Phan Gia Bao Le | Yuepeng Du | Thong Nguyen
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Fully complete implementation and error free, Final Tests, Automated placement of tiles at end of round, but no scoring | Group Report Written, Bug fixes of clear the broken line after each round, Bug fixes of miscalculation in score | Fully complete implementation and error free, Full error checking of user prompt, Bug fixes in loading game, Bug fixes of miscalculation in score
|  |  | Full error checking of user prompt |  | Issues
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes
Final Tests
Group Report Written
|  | Progress | On-track